## Sheet1
Activity | March |  |  | April |  |  |  | May
| 2nd W | 3rd W | 4th W | 1st W | 2nd W | 3rd W | 4th W | 1st W | 2nd W
Installations and SetUp | Sowmya
Performing MR on sample data set in Local machine |  | Evan
Scripting to achieve Goal |  |  | Sowmya | Evan
Performing experiment on cluster |  |  |  |  | Sowmya | Mid-Term | Evan
Project presentation and Report preparation | [6 empty] | Evan | Sowmya
Report Submission | [8 empty] | Sowmya/Evan