## Sheet1
Activity | March |  |  | April |  |  |  | May
| 2nd W | 3rd W | 4th W | 1st W | 2nd W | 3rd W | 4th W | 1st W | 2nd W
Installations and SetUp, getting the sparks running on local machine | Sowmya
Performing MR on sample data set in Local machine |  | Evan
Reseraching about Page Rank algorithm and its implemetations |  |  | Sowmya | Evan
Installing HDFS, experimenting with data distribution on cluster |  |  |  |  | Sowmya | Mid-Term | Sowmya
Getting the the algorithm running on the cluster on the entire data set | [6 empty] | Evan
Project presentation and Report preparation | [7 empty] | Sowmya/Evan
Report Submission | [8 empty] | Sowmya/Evan